## Control Sheet
Scenario Id | Sub Scenario Id | Description | Expected Result | Assigned To | Reviewed by | Weekday - 1 | [6 empty] | Weekday - 2 | [6 empty] | Weekday - 3 | [6 empty] | Weekday - 4 | [6 empty] | Start Date | End Date
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7
1 |  | Home Page |  | Ranvijay | Rajesh Sir | [28 empty] | 14/1/2020 | 15/1/2020 | bar: Weekday - 2 5 to Weekday - 2 6
| 1.1 | Authentication | User Should get Authenticated | Ranvijay | Rajesh Sir | [28 empty] | 14/1/2021
| 1.1.1 | User Registration | New User Should get Registered | Ranvijay | Rajesh Sir | [28 empty] | 14/1/2022
| 1.1.2 | User Sign In | User Should be allowed to Login | Ranvijay | Rajesh Sir | [28 empty] | 14/1/2023
2 |  | Selecting 'Pickup' Location |  | Ranvijay | Rajesh Sir | [28 empty] | 14/1/2020 | 15/1/2020 | bar: Weekday - 2 6
| 2.1 | Mobile Phones | User Should Navigate to Mobile Phones Page | Ranvijay | Rajesh Sir | [28 empty] | 14/1/2021 | 15/1/2021
| 2.2 | Mobile Category | User should be Provided with 2 category | Ranvijay | Rajesh Sir | [28 empty] | 14/1/2022 | 15/1/2022
| 2.2.1 | Mobile Cell Phones | User should be provided with Choices | Ranvijay | Rajesh Sir | [28 empty] | 14/1/2023 | 15/1/2023
| 2.2.2 | Mobile Accessories | User should be provided with Choices | Ranvijay | Rajesh Sir | [28 empty] | 14/1/2024 | 15/1/2024
3 |  | Selecting 'Drop' Location |  | Ranvijay | Rajesh Sir | [28 empty] | 14/1/2020 | 15/1/2020 | bar: Weekday - 2 5 to Weekday - 2 6
3 | 3.1 | Uploading Files | Samsung option should provide Refine Options | Ranvijay | Rajesh Sir | [28 empty] | 14/1/2026 | 15/1/2026
4 |  | Choose Cab Categories |  | Ranvijay | Rajesh Sir | [28 empty] | 14/1/2020 | 15/1/2020
5 |  | Payment Option |  | Ranvijay | Rajesh Sir | [28 empty] | 14/1/2020 | 15/1/2020
6 |  | Book Cab |  | Ranvijay | Rajesh Sir

## Test Scenario
Scenario Id | Sub Scenario Id | Description | Expected Result
1 |  | Home Page
| 1.1 | Choosing City Taxi | Travelling within the city Ride selected
| 1.2 | Outstation Ride | Travelling from one city to other Cabs selected
| 1.3 | Rentals Option | Ride yourself Option Appears
2 |  | Selecting 'Pickup' Location
| 2.1 | PinPoint on Map/Choose from suggested acc. to typed place | Pickup Location Selected
| 2.1.1 | Select the desired locations | Input Location Set
3 |  | Selecting 'Drop' Location
| 3.1 | PinPoint on Map/Choose from suggested acc. to typed place | Drop Location Set
| 3.1.1 | Select the desired locations | Input Location Set
4 |  | Choose Cab Categories
| 4.1 | Cabs of Different Capacity and Size available | Cabs selected acc. to No. of persons traveling
| 4.2 | Look for Mini, Micro, XL, Share etc
5 |  | Payment Option
| 5.1 | Choose Cash
| 5.1.1 | Choose Ola Money
| 5.1.2 | Choose any other payment Option | Preferred Payment Option Set
6 |  | Book Cab
| 6.1 | Searching for nearby cabs | Booked Cab displayed with OTP and Driver Details
| 6.2 | Enter using Login Options which is Mob. No. | Details sent to Registered Mob. No.

## Test Script
Scenario Id | Sub Scenario Id | Script ID/Step | Description | Expected Result
1
| 1.1 | Home Page |  | https://www.olacabs.com/
|  | 1 | City Taxi | Selected for cabs within the city
|  | 2 | Outstation rides | Selected for cabs from one cities to other city
|  | 3 | Rentals Options | Cabs for self driving options displayed
2 |  | Selecting 'Pickup' Location
| 2.1 | Enter 'FROM' Address | User should navigate to location tab
|  | 1 | Desired Address for pickup displayed | Preferred Location Selected
|  | 2 | Chicked from suggested displayed Address | Green color PinPoined to selected address
3 |  | Selecting 'Drop' Location
| 3.1 | Enter 'TO' Address | User should navigate to location tab
|  | 1 | Selection of desired Address to drop | Preferred Location Selected
|  | 2 | Selection from suggested displayed Address | Red color PinPoined to selected address
|  | 3 | Now click on search Cabs | Cabs with different capacities displayed
4 |  | Choose Cab Categories
| 4.1 | Auto , Micro, Mini, SUV , Share etc
|  | 1 | Mini, Micro Cabs for 1-4 people | Preferred Cabs Selected
|  | 2 | XL for 5 to 7 people | Preferred Cabs Selected
|  | 3 | Share ride with others | Preferred Cabs Selected
5 |  | Payment Option
| 5.1 | Choose Cash, Ola Money , Google Pay etc
|  | 1 | Choose Cash Option for post payment | Payment after the ride is over
|  | 2 | Choose Prepiad Options | Pre Selected the payment options
6 |  | Book Cab
| 6.1 |  |  | The desired ride is booked
|  | Ride Details display | Driver Name , Car Details and OTP | Driver Name , Car Details and OTP is displayed