## Control Sheet
Scenario Id | Sub Scenario Id | Description | Expected Result | Assigned To | Reviewed by | Weekday - 1 | [6 empty] | Weekday - 2 | [6 empty] | Weekday - 3 | [6 empty] | Weekday - 4 | [6 empty] | Start Date | End Date
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7
1 |  | Home Page |  | Krishna Priya | Rajesh | [28 empty] | 2019-03-09 | 2019-04-09 | bar: Weekday - 1 3
| 1.1 | Authentication | User Should get Authenticated
| 1.1.1 | User Registration | New User Should get Registered
| 1.1.2 | User Sign In | User Should be allowed to Login
2 |  | Explore Page |  | Krishna Priya | Rajesh | [28 empty] | 2019-03-09 | 2019-04-09 | bar: Weekday - 1 3
| 2.1 | Mobile Phones | User Should Navigate to Mobile Phones Page
| 2.2 | Mobile Category | User should be Provided with 2 category
| 2.2.1 | Mobile Cell Phones | User should be provided with Choices
| 2.2.2 | Mobile Accessories | User should be provided with Choices
3 |  | Enrollment Page |  | Krishna Priya | Rajesh | [28 empty] | 2019-03-09 | 2019-04-09 | bar: Weekday - 1 3
| 3.1 | Click on Samsung option | Samsung option should provide Refine Options
4 |  | Payment Page |  | Krishna Priya | Rajesh | [28 empty] | 2019-03-09 | 2019-04-09 | bar: Weekday - 1 3
5 |  | My Courses Page |  | Krishna Priya | Rajesh | [28 empty] | 2019-03-09 | 2019-04-09 | bar: Weekday - 1 3

## Test Scenario
Scenario Id | Sub Scenario Id | Description | Expected Result
1 |  | Home Page
| 1.1 | Authentication | User Should get Authenticated
| 1.1.1 | User Registration | New User Should get Registered
2 |  | Explore Page
| 2.1 | Course Search | List of courses available should be displayed
| 2.1.1 | Course Selection | Page should be redirected to selected course enrollmentpage
3 |  | Enrollment Page
| 3.1 | Auditing Course | User should get access to course with out graded assesment and certificate
| 3.2 | Purchase Course | Page should be redirected to Payment Page
4 |  | Payment Page
| 4.1 | Payment Details | User should enter the payment details
| 4.2 | Payment Confirmation | User should get access to course with graded assesment and certificate
5 |  | My Courses Page
| 5.1 | Book Mark Course | User should be able to Book Mark the course.
| 5.2 | Resume Course | Course should start from Book Marked point
| 5.3 | View Status | Percentage of course completed should be displayed.
| 5.4 | With Draw From Course | User should be able to with draw from course before 7 days from enrollment.
| 5.5 | Download Course Completion Certificate | User should be able to download pdf of course completed certificate
| 5.6 | Submit Assesment | Assesment should be submitted for grading.

## Test Script
COURSEERA.ORG
Scenario Id | Sub Scenario Id | Script ID/Step | Description | Expected Result
1 |  |  | Home Page
| 1.1 |  | Authentication | User Should get Authenticated
|  | 1 | Click on Login | On click page should redirect to login page
|  | 2 | Enter username/Gmail | Accepts Valid User name/Gmail
|  | 3 | Enter Password | Accepts Valid Password
|  | 4 | Click on Login | Successfully Logged in
| 1.1.1 |  | User Registration | New User Should get Registered
|  | 1 | Click on login button | Redirects to the login page
|  | 2 | Click on "Sign Up" page | Redirects to the Sign Up page
|  | 3 | Enter User Name | Accepts Valid User Name
|  | 4 | Enter Email Id | Accepts Valid Email Id
|  | 5 | Enter Password | Accepts Valid Password
|  | 6 | Click on Sign up button | New user successfully registered
2 |  |  | Explore Page
| 2.1 |  | Course Search | List of courses available should be displayed
|  | 1 | Click on All Courses Tab | Displays List of Domains
|  | 2 | Click on Perticular Domain | Displays List of available Courses in selected Domain
| 2.1.1 | 2.2 | Course Selection | Page should be redirected to selected course enrollmentpage
|  | 1 | Click on Perticular Course | Page is redirected to selected course enrollmentpage
3 |  |  | Enrollment Page
| 3.1 |  | Auditing Course | User should get access to course with out graded assesment and certificate
|  | 1 | Click on Audit Button | Page redirects to Perticular course with out graded assesment and certificate
| 3.2 |  | Purchase Course | Page should be redirected to Payment Page
|  | 2 | Click on Purchase Couse Button | Page is redirected to Payment Page
4 |  |  | Payment Page
| 4.1 |  | Payment Details | User should enter the payment details
|  | 1 | Enter Name On Card | Accepts valid Name
|  | 2 | Enter Card Number | Accepts valid Card Number
|  | 3 | Enter Expire Date | Accepts Valid Date
|  | 4 | Enter CVV Number | Accepts Valid CVV number
|  | 5 | Enter Country | Accepts Valid Country Name
|  | 6 | Click on Make Payment | Page is redirected to Payment confirmation page
| 4.2 |  | Payment Confirmation | User should get access to course with graded assesment and certificate
|  | 1 | Enter OTP send to mobile | Accepts Valid OTP
|  | 2 | Click on Confirm Payment | Page is redirected to course with graded assesment and certificate
5 |  |  | My Courses Page
| 5.1 |  | Book Mark Course | User should be able to Book Mark the course.
|  | 1 | Click on Book mark symbol | Course is book marked at thet point
| 5.2 |  | Resume Course | Course should start from Book Marked point
|  | 1 | Click on Resume button | Course is started from Book Marked point
| 5.3 |  | View Status | Percentage of course completed should be displayed.
|  | 1 | Click on View Status button | Displays percentage of course completed
| 5.4 |  | WithDraw From Course | User should be able to with draw from course before 7 days from enrollment.
|  | 1 | Click on with draw button | Page displays valid resons for with drawel
|  | 2 | Select valid reason | valid reason is selected
|  | 3 | Click on submit button | with draw request is submitted for approval
| 5.5 |  | Download Course Completion Certificate | User should be able to download pdf of course completed certificate
|  | 1 | Click on Download Certificate Button | Certificate is downloaded in PDF format.
| 5.6 |  | Submit Assesment | Assesment should be submitted for grading.
|  | 1 | Click on submit assesment | File upload window is displayed.
|  | 2 | Select file to be uploaded | File is uploaded successfully for grading.

## Test Script Execution
Scenario Id | Sub Scenario Id | Script ID/Step | Description | Expected Result | Actual | Conclusion
1 |  |  | Home Page
| 1.1 |  | Authentication | User Should get Authenticated
|  | 1 | Click on Login | On click- page should redirect to login page | On click- page redirected to login page | PASS
|  | 2 | Enter username/Gmail | Accepts Valid User name/Gmail | Accepted Valid User name/Gmail | PASS
|  | 3 | Enter Password | Accepts Valid Password | Accepted Valid Password | PASS
|  | 4 | Click on Login | Successfully Logged in | Successfully Logged in | PASS
| 1.1.1 |  | User Registration | New User Should get Registered
|  | 1 | Click on login button | Redirects to the login page | Redirected to the login page | PASS
|  | 2 | Click on "Sign Up" page | Redirects to the Sign Up page | Redirected to the Sign Up page | PASS
|  | 3 | Enter User Name | Accepts Valid User Name | Accepted Valid User Name | PASS
|  | 4 | Enter Email Id | Accepts Valid Email Id | Accepted Valid Email Id | PASS
|  | 5 | Enter Password | Accepts Valid Password | Accepted Valid Password | PASS
|  | 6 | Click on Sign up button | New user successfully registered | Failed to register new user | FAIL
2 |  |  | Explore Page
| 2.1 |  | Course Search | List of courses available should be displayed
|  | 1 | Click on All Courses Tab | Displays List of Domains | Displayed List of Domains | PASS
|  | 2 | Click on Perticular Domain | Displays List of available Courses in selected Domain | Displayed List of available Courses in selected Domain | PASS
| 2.1.1 | 2.2 | Course Selection | Page should be redirected to selected course enrollmentpage
|  | 1 | Click on Perticular Course | Page is redirected to selected course enrollmentpage | Page is redirected to selected course enrollmentpage | PASS
3 |  |  | Enrollment Page
| 3.1 |  | Auditing Course | User should get access to course with out graded assesment and certificate
|  | 1 | Click on Audit Button | Page redirects to Perticular course with out graded assesment and certificate | Page redirected to Perticular course with graded assesment and certificate | FAIL
| 3.2 |  | Purchase Course | Page should be redirected to Payment Page
|  | 2 | Click on Purchase Couse Button | Page is redirected to Payment Page | Page is redirected to Payment Page | PASS
4 |  |  | Payment Page
| 4.1 |  | Payment Details | User should enter the payment details
|  | 1 | Enter Name On Card | Accepts valid Name | Accepted valid Name | PASS
|  | 2 | Enter Card Number | Accepts valid Card Number | Accepted valid Card Number | PASS
|  | 3 | Enter Expire Date | Accepts Valid Date | Accepted Valid Date | PASS
|  | 4 | Enter CVV Number | Accepts Valid CVV number | Accepted Valid CVV number | PASS
|  | 5 | Enter Country | Accepts Valid Country Name | Accepted Valid Country Name | PASS
|  | 6 | Click on Make Payment | Page is redirected to Payment confirmation page | Page is redirected to Payment confirmation page | PASS
| 4.2 |  | Payment Confirmation | User should get access to course with graded assesment and certificate
|  | 1 | Enter OTP send to mobile | Accepts Valid OTP | Accepts Valid OTP | PASS
|  | 2 | Click on Confirm Payment | Page is redirected to course with graded assesment and certificate | Page is redirected to course with out graded assesment and certificate | FAIL
5 |  |  | My Courses Page
| 5.1 |  | Book Mark Course | User should be able to Book Mark the course.
|  | 1 | Click on Book mark symbol | Course is book marked at that point | Course is book marked at that point | PASS
| 5.2 |  | Resume Course | Course should start from Book Marked point
|  | 1 | Click on Resume button | Course is started from Book Marked point | Course started from begining point of the last viewed vedio | FAIL
| 5.3 |  | View Status | Percentage of course completed should be displayed.
|  | 1 | Click on View Status button | Displays percentage of course completed | Displayed percentage of course completed | PASS
| 5.4 |  | WithDraw From Course | User should be able to with draw from course before 7 days from enrollment.
|  | 1 | Click on with draw button | Page displays valid resons for with drawel | Page displayed valid resons for with drawel | PASS
|  | 2 | Select valid reason | valid reason is selected | valid reason is selected | PASS
|  | 3 | Click on submit button | with draw request is submitted for approval | with draw request is submitted for approval | PASS
| 5.5 |  | Download Course Completion Certificate | User should be able to download pdf of course completed certificate
|  | 1 | Click on Download Certificate Button | Certificate is downloaded in PDF format. | Certificate is downloaded in PDF format. | PASS
| 5.6 |  | Submit Assesment | Assesment should be submitted for grading.
|  | 1 | Click on submit assesment | File upload window is displayed. | File upload window is not displayed. | FAIL
|  | 2 | Select file to be uploaded | File is uploaded successfully for grading. | Failed to upload assessment file for grading | FAIL

## Defect
Scenario Id | Sub Scenario Id | Script ID/Step | Defect ID | Defect Description | Description | Expected Result | Severity
1 |  |  |  |  | Home Page
| 1.1.1 |  |  |  | User Registration | New User Should get Registered
|  | 6 |  |  | Click on Sign up button | Registration successful
|  |  | #D1010 | Unable to register new user | On clicking sign up button no action is done | On clicking sign up button user should be able to login and get registration successful message | SHOW STOPPER
3 |  |  |  |  | Enrollment Page
| 3.1 |  |  |  | Auditing Course | User should get access to course with out graded assessment and certificate
|  | 1 |  |  | Click on Audit Button | Page redirects to Perticular course with out graded assesment and certificate
|  |  | #D5445 | Failed to access course in audit mode | On clicking audit button course released with purchase course rights | On clicking audit button course should be released in audit mode rights | HIGH
4 |  |  |  |  | Payment Page
| 4.2 |  |  |  | Payment Confirmation | Payment successful and User should get access to course with graded assessment and certificate
|  | 2 |  |  | Click on Confirm Payment | Page redirects to Perticular course with graded assesment and certificate
|  |  | #D5467 | Failed to access course in purchase mode | On clicking confirm button course released with only audit rights | On clicking confirm button course should be released with purchase course rights | HIGH
5 |  |  |  |  | My Courses Page
| 5.2 |  |  |  | Resume Course | Course should start from Book Marked point
|  | 1 |  |  | Click on Resume button | Course is started from Book Marked point
|  |  | #D4353 | Unable to start course from bookmarked point | On clicking resume Course started from begining point of the last viewed vedio | On clicking resume button Course should start from Book Marked point | LOW
5 |  |  |  |  | My Courses Page
| 5.6 |  |  |  | Submit Assesment | Assesment should be submitted for grading.
|  | 1 |  |  | Click on submit assesment | File upload window is displayed.
|  |  | #D7878 | Failed to upload assessment file for grading | On clicking submit button no action is done | On clicking submit button File upload window should be displayed. | MEDIUM